Hixson-Lied College of Fine and Performing Arts

# undergraduate STUDENT

# creative research grant

# Application

2008-2009

Please enter the required information by clicking on the grey text boxes. When completed, save this file as CreResAppYOURNAME.doc and send it as an attachment in an e-mail to the Department Director/Chair.

This application will not be considered without the supporting letter from the faculty sponsor and samples of previous work.

STUDENT NAME: John Albrecht	DATE: 9/15/2008	E-MAIL:

LOCAL ADDRESS:	CITY, ST:	ZIP:

LOCAL PHONE:

PERMANENT ADDRESS:	CITY, ST:	ZIP:

PERMANENT PHONE:

YEAR IN SCHOOL: 	MAJOR: 	AREA OF STUDY: Film and New Media

SPONSORING FACULTY MEMBER: Sharon Teo

RÉSUMÉ OF COMPLETED PROJECTS

LIST PREVIOUSLY COMPLETED WORK: PROJECTS, PERFORMANCES, EXHIBITIONS, ETC.

(INCLUDE DATES).

Please see attached resume.

PROJECT PROPOSAL

PROJECT TITLE:

"No Orange" Set Design

PROJECT DESCRIPTION:

IN 300 TO 500 WORDS DESCRIBE THE PROJECT AND ITS OBJECTIVE(S), YOUR PLAN TO CARRY OUT THE PROJECT (INCLUDE A TIMELINE), AND HOW THE PROJECT WILL ADVANCE YOUR ARTISTIC AND SCHOLARLY CAPABILITIES.

Before my graduation in May, I will be directing a short film entitled "No Orange" as my senior project in the Film and New Media program.  The film will articulate a very personal theme, demanding strict artistic discipline to guide my passion for the project.

No Orange examines the role of addiction in a person's life, suggesting that our weaknesses and strengths are not always easy to identify.  The main character leads a life of escapism, pursuing self-destructive behaviors as a means to overcome a persistent pain.  Faced with a choice to continue on her desolate path or become well, she challenges herself to remove every addiction and dependency from her life.  Though her cleanse brings some level of happiness and gain, she begins to ignore the consequences that independence and perfection can afflict.  The character must ultimately decide between freedom in isolation or finding new strength in admitting weakness.

Due to demands of the script, I need to build a set for the inside of a studio apartment.  The set's realism, and its ability to be photographed from all angles, requires significant costs for building materials, construction, and furnishing/set decoration.  Unlike a theatrical set, the film set must be completed on all sides and built with movable walls to accommodate the camera and crew.  Aid from the HLCFPA will ensure that the set will not be compromised in quality or depend on loans.

The film's Production Designer and I are currently developing floorplans for the set and have begun to enlist students for a build crew.

-October 2008: Set design is finalized.

-November 2008: Perspective drawings and construction schematics are created.  Set build is scheduled as materials and    fixtures are acquired.

-December 2008: Construction begins at the end of Fall Semester.

-January 2009: Filming begins, the schedule lasting a week to ten days.  The set will then be returned to the school for further use; since the interior set features flats with basic doors and windows, the pieces can be employed for future projects.

-February 2009: Editing begins.

-April 2009: Editing is completed.  The film is exhibited, submitted to film festivals such as the Student Academy Awards.

No Orange imports a comprehensive personal effort, drawing on all of my stage and film training.  The project also offers an important step forward in my development as a filmmaker.  Working within the flexibility of a studio environment, I will engage the difficulties of a design/build process within a creative team determined to produce a work of professional quality.

The project presents a unique opportunity to involve theatre and film students from a variety of emphases and disciplines, necessitating collaboration between those who study design, construction, painting, cinematography, performance, and direction.  With the school film scheduled to begin shooting in Summer 2009, the production design requirements of No Orange would provide practical experience to students who wish to be involved with the school film under a similar set design capacity.

Please see attached budget for detailed figures.

BUDGET INFORMATION

##### PLEASE PROVIDE AN ESTIMATE OF YOUR TOTAL ANTICIPATED EXPENSES AS FOLLOWS:

Materials (Itemized)

Flats	$ 489.03

Flooring and Fixtures	$ 245.65

Hardware	$ 114.78

Tax and Contingency	$ 186.88

Services (Itemized)

Studio Rental (Lights On Studio)	$ 2050

$

$

$

Travel (Itemized)

$

$

$

$

Other (Itemized)

$

$

$

$

TOTAL EXPENSES	$ 3086

IF YOU ANTICIPATE ANY OTHER SOURCE OF FUNDING FOR THIS ACTIVITY, INDICATE THE

AMOUNT:  $ 2550

AND SOURCE:

Personal funds

Paul Steger, JCSOTF

See Attached

<END OF APPLICATION>